CHAINLENS

MVP Specification

Scope, milestones, technical architecture, launch criteria, and success definition

MVP Target: Week 8 from kickoff Team Size: 3 engineers + 1 PM ¦ Tech: Next.js + Ponder + PostgreSQL ¦ Launch: Public beta April 2026 ¦ Version 1.0 ¦ Working Document

Table of Contents

# 1. MVP Philosophy

Core Principle The Seraph MVP is the minimum product that lets a DeFi user track any cross-chain transaction, regardless of protocol, in one place. Nothing more. Nothing less.

The MVP exists to answer one question: 'Is there real demand for a unified cross-chain explorer?' We test this by shipping the smallest possible version that covers the core use case, then measuring retention and usage signals.

## What MVP Means for Seraph

| MVP Is... | MVP Is NOT... |
| --- | --- |
| Functional tx search across 8 core protocols | All 14 protocols on Day 1 |
| Accurate data for indexed protocols | 100% historical data from chain genesis |
| Simple, clean UI that works on mobile | Polished, pixel-perfect design system |
| Public REST API with basic auth | Full API portal with Stripe billing |
| Real-time Chain Flow Map on homepage | Every analytics dashboard |
| Free to use — no login required | Wallet portfolio, alerts, Pro tier |
| Deployed and publicly accessible | Scaling infrastructure for 1M users |

The Anti-Feature Rule For every feature added to the MVP scope, we must remove one. If it doesn't directly answer 'can the user find their cross-chain transaction?', it does not belong in the MVP. We can add features after launch — we cannot subtract complexity once users depend on it.

# 2. MVP Scope

## 2.1 IN Scope — Ship Before Launch

| Feature | Why It's In Scope | Effort |
| --- | --- | --- |
| Transaction search by hash (8 protocols) | Core use case — must work on Day 1 | XL |
| Address transaction history (8 protocols) | Users need to check their own wallet | L |
| Transaction detail page | The sharable, viral unit of Seraph | L |
| Real-time status tracking (PENDING -> CONFIRMED) | The primary reason users come back to the page | L |
| Chain explorer view (recent txs per chain) | Browse mode — SEO and discovery | M |
| Live Chain Flow Map (homepage) | First impression — explains what Seraph does instantly | M |
| Public REST API (GET /tx, GET /address/txs) | Developers must be able to integrate on Day 1 | L |
| Mobile-responsive design | Bridge status is checked on mobile | M |
| Protocol health indicators | Users need to know if a protocol is degraded before trusting data | S |
| Search by ENS name | Core user behavior — many users know ENS, not raw address | S |
| Direct links: source tx -> native block explorer | Developers and power users need to verify on-chain | S |
| Basic analytics: volume by protocol (24H) | Shows Seraph has data; drives press coverage on launch | M |

## 2.2 OUT of Scope — Post-MVP

| Feature | Why It's Post-MVP | Target Phase |
| --- | --- | --- |
| Wallet portfolio view (connect wallet) | Needs auth, wallet connect, data aggregation — complexity | Phase 2 |
| Bridge alerts / notifications | Needs notification infra, user accounts, preferences | Phase 2 |
| API key portal with Stripe billing | Revenue feature — validate demand before monetizing | Phase 2 |
| Webhooks | Needs delivery infra, retry logic, user management | Phase 3 |
| All 14 protocols (6 extra) | 8 covers >90% of volume; add more based on user requests | Phase 2 |
| Historical data > 90 days | Storage cost; users care about recent and current txs | Phase 3 |
| Entity / wallet labels | Needs data partnership or crowdsourced labeling system | Phase 3 |
| AML/compliance API | Enterprise product — entirely separate build | Year 2 |
| White-label EaaS | B2B sales motion — not relevant for consumer launch | Year 2 |
| Native mobile apps (iOS/Android) | PWA is sufficient for MVP; native apps post-PMF | Phase 4 |
| User accounts / login | Creates friction; MVP should be zero-login | Phase 2 (optional) |

# 3. MVP Protocol Coverage (8 Protocols)

We index the 8 protocols that cover >90% of cross-chain bridge volume. This is the minimum set to be credible as a 'unified' explorer. The remaining 6 protocols will be added in Phase 2 based on user demand signals.

| Protocol | Why Include in MVP | Est. % of Market Volume | Indexing Approach |
| --- | --- | --- | --- |
| LayerZero V2 | #1 by message volume; most dev integrations | ~25% | Ponder.sh — SendPacket events |
| Wormhole | $54B lifetime; dominant on Solana | ~20% | Wormhole VAA API + Ponder |
| Across Protocol | Fastest bridge; strong UX reputation | ~15% | Ponder.sh — FilledRelay events |
| Stargate V2 | Largest TVL bridge; OFT standard | ~15% | Ponder.sh — OFTSent events |
| Axelar GMP | Top Cosmos-EVM bridge; 45+ chains | ~10% | Axelar REST API + indexer |
| CCTP (Circle) | Native USDC; regulated, trusted | ~8% | Ponder.sh — MessageSent events |
| IBC Protocol | All Cosmos chains; cannot ignore | ~5% | IBC LCD API + tendermint |
| Hop Protocol | OG L2 bridge; long-tail users still active | ~2% | Ponder.sh — TransferSent events |

Coverage Note 8 protocols covering ~90% of volume is the right MVP scope. Range (our closest competitor) covers 4 protocols. Launching with 8 immediately establishes Seraph as the broadest cross-chain explorer available.

# 4. MVP Technical Architecture

## 4.1 System Overview

Seraph MVP uses a 3-layer architecture: Indexing Layer (protocol-specific adapters), Data Layer (PostgreSQL + Redis cache), and Presentation Layer (Next.js frontend + REST API). This is the minimum viable architecture that can scale to 1M daily queries without a full rewrite.

| Layer | Technology | Role | Why This Choice |
| --- | --- | --- | --- |
| Indexing | Ponder.sh | Real-time EVM event indexing per protocol | Type-safe, built for EVM, handles reorgs, schema migrations |
| Indexing (non-EVM) | Custom REST pollers | Wormhole VAA API, IBC LCD, Axelar API | Ponder is EVM-only; REST pollers for non-EVM chains |
| Database | PostgreSQL + TimescaleDB | Persistent tx storage, time-series queries | TimescaleDB handles time-series efficiently; familiar SQL |
| Cache | Redis | In-memory cache for hot queries (tx by hash, address txs) | < 10ms response for cached queries; reduces DB load |
| API | Node.js + Fastify | REST API server, rate limiting, auth | Fastify is fastest Node HTTP server; built-in JSON schema |
| Frontend | Next.js 14 (App Router) | SSR explorer pages, React components | ISR for static pages (chain explorer); SSR for dynamic (tx detail) |
| Styling | Tailwind CSS + shadcn/ui | Component library | Speed of development; consistent design system |
| Web3 | Wagmi v2 + Viem | Wallet connection (post-MVP), ENS resolution | Industry standard for React + EVM |
| Charts | Recharts + D3.js | Analytics charts + Chain Flow Map | Recharts for standard charts; D3 for custom SVG network graph |
| Infra | Railway or Render (MVP) | Simple deployment, managed DB | Low ops overhead for small team; migrate to AWS/GCP at scale |
| Real-time | WebSocket (ws library) | Live tx status updates on tx detail page | Push updates to avoid polling; auto-fallback to polling |

## 4.2 Data Flow

How a transaction goes from on-chain event to Seraph UI in under 5 seconds:

Data Flow: Bridge TX -> Seraph UI - User initiates bridge on source chain (e.g., bridge ETH on Ethereum via Across) - Across Protocol emits DepositV3 event on Ethereum - Ponder.sh adapter picks up event within 1-3 blocks (~15 seconds on Ethereum) - Adapter normalizes to Seraph schema: { txHash, protocol: 'across', status: 'pending', sourceChain: 'ethereum', destChain: 'arbitrum', asset: 'ETH', amount: '1.5', ... } - Normalized tx written to PostgreSQL, indexed on txHash + address + protocol - Redis cache updated: key = txHash, value = serialized tx JSON, TTL = 60s - User searches tx hash on Seraph -> Redis hit -> response in < 50ms - Destination chain confirms: RelayedDeposit event on Arbitrum - Ponder updates tx status to 'confirmed' in PostgreSQL + Redis - WebSocket pushes status update to user's browser: status changes from PENDING to CONFIRMED in real time

Latency Target Source tx: indexed within 30 seconds of on-chain confirmation. Destination tx: indexed within 30 seconds of destination confirmation. Total: user sees CONFIRMED status within 60 seconds of the bridge completing. Target is 30 seconds by launch.

## 4.3 Database Schema (Simplified)

| Table | Key Columns | Indexes | Notes |
| --- | --- | --- | --- |
| bridge_txs | id, source_tx_hash, dest_tx_hash, protocol, source_chain, dest_chain, asset, amount_raw, amount_usd, fee_usd, status, created_at, updated_at | source_tx_hash, dest_tx_hash, (protocol + source_chain), created_at | Core table; one row per bridge attempt |
| tx_steps | id, bridge_tx_id, step_order, step_type, chain, block_number, tx_hash, timestamp, status | bridge_tx_id, tx_hash | Each hop/step of multi-step bridges |
| address_txs | id, address, bridge_tx_id, direction (in/out) | address + direction, address + protocol | Join table: one row per address involved in a tx |
| protocols | id, slug, name, chain_coverage, status, avg_confirm_time_seconds | slug | Protocol metadata; updated hourly |
| price_snapshots | id, asset, chain, price_usd, timestamp | asset + timestamp | For USD amount calculation at time of tx |

# 5. MVP Milestones (8-Week Build Plan)

## Week-by-Week Breakdown

| Week | Milestone / Deliverable | Owner | Status |
| --- | --- | --- | --- |
| W1 | Project setup: monorepo, DB schema, Ponder config, base API structure, CI/CD pipeline. First Ponder adapter: Across Protocol (simplest schema). Admin indexer dashboard (internal). | Eng Lead | Pending |
| W2 | Ponder adapters: LayerZero V2, CCTP (Circle). REST API endpoints: GET /tx/{hash}, GET /address/{addr}/txs. Internal test harness with known mainnet txs. Data accuracy target: 99%. | Full Team | Pending |
| W3 | Ponder adapters: Stargate V2, Hop Protocol. Non-EVM poller: Wormhole VAA API (polling mode, not event-based). Protocol adapter framework documented for future contributors. Redis caching layer deployed. | Full Team | Pending |
| W4 | Frontend: Next.js project setup, Tailwind + shadcn/ui. Search bar component, tx detail page (design + data). Chain Flow Map animation (React component, mock data first). Mobile responsive check. | Frontend Eng | Pending |
| W5 | Non-EVM pollers: IBC LCD API, Axelar REST API. Frontend: address page, chain explorer page. Wire frontend to real API (replace mock data). ENS resolution integration. Protocol health endpoint. | Full Team | Pending |
| W6 | Integration Week: Chain Flow Map wired to real API data. WebSocket server for live tx status updates. End-to-end test: bridge a real tx on testnet, confirm it appears on Seraph within 30 seconds. Performance test: target < 200ms API p95. | Full Team | Pending |
| W7 | QA Week: Manual testing of all 8 protocol adapters with real mainnet txs. Mobile QA on iOS Safari and Android Chrome. SEO: meta tags, OpenGraph images per tx, sitemap. Bug fixes. Load test: 100 concurrent users. | QA + Full Team | Pending |
| W8 | Launch prep: Production deployment to Railway/Render. Domain setup (chainlens.io). Analytics (Plausible or PostHog). Status page (statuspage.io). Public beta launch: Product Hunt, protocol Discord channels, Twitter thread. | PM + Full Team | Pending |

## Pre-Launch Checklist

| Category | Item | Owner | Done? |
| --- | --- | --- | --- |
| Infrastructure | Production DB deployed with backups | Eng Lead | [ ] |
| Infrastructure | Redis cache deployed + monitored | Eng Lead | [ ] |
| Infrastructure | CDN configured for static assets | Eng Lead | [ ] |
| Infrastructure | SSL/TLS certificates on all domains | Eng Lead | [ ] |
| Infrastructure | Status page live at status.chainlens.io | PM | [ ] |
| Data | All 8 protocol adapters tested with real mainnet txs | Full Team | [ ] |
| Data | Data accuracy validated: spot check 50 known txs | Eng Lead | [ ] |
| Data | Historical data loaded: last 30 days for all 8 protocols | Eng Lead | [ ] |
| Frontend | All pages pass Lighthouse score > 80 (mobile) | Frontend | [ ] |
| Frontend | No horizontal scroll on any page (mobile) | Frontend | [ ] |
| Frontend | 404 and error pages designed and deployed | Frontend | [ ] |
| SEO | Meta tags on all key pages (tx, address, chain) | Frontend | [ ] |
| SEO | OpenGraph images for social sharing | Frontend | [ ] |
| SEO | Sitemap.xml submitted to Google Search Console | PM | [ ] |
| API | API documentation published at docs.chainlens.io | Eng Lead | [ ] |
| API | Rate limiting confirmed working at free tier | Eng Lead | [ ] |
| Analytics | Product analytics (PostHog or Plausible) installed | PM | [ ] |
| Legal | Privacy policy + terms of service published | PM | [ ] |
| Community | Discord server created, invite link live | PM | [ ] |
| Launch | Product Hunt page scheduled for launch day | PM | [ ] |

# 6. MVP Launch Success Criteria

Definition of Launch Success Seraph MVP is a success if, within 30 days of launch, we have 1,000 weekly active users who are returning because the product solved their real problem — NOT because of a gimmick, airdrop promise, or marketing hype.

## Quantitative Success Criteria (30 days post-launch)

| Metric | Minimum Success | Strong Success | Exceptional |
| --- | --- | --- | --- |
| Weekly Active Users | 500 WAU | 1,000 WAU | 2,000 WAU |
| Total Unique Visitors | 5,000 | 10,000 | 25,000 |
| Txs Indexed/Day | 50K | 100K | 500K |
| API Calls/Day | 500 | 2,000 | 10,000 |
| 30-Day Retention | >10% | >20% | >35% |
| Discord Members | 200 | 500 | 1,000 |
| Protocol Discord Mentions | 5 | 20 | 50 |
| NPS Score | >20 | >35 | >50 |

## Qualitative Success Signals

- Unsolicited Twitter posts showing Seraph finding a stuck bridge tx

- Protocol team (LayerZero, Wormhole, etc.) mentions Seraph in their Discord

- DeFi newsletter includes Seraph in 'useful tools' roundup

- Developer integrates Seraph API into their dApp within 30 days

- Users report Seraph found their tx when the protocol's own explorer couldn't

## Kill Criteria (When to Pivot)

Pivot Signal If after 60 days we have < 200 WAU AND < 5% 30-day retention AND no organic word-of-mouth, we have not found product-market fit. This means the problem is either not painful enough, or Seraph doesn't solve it well enough. We should do 20+ user interviews before deciding to pivot.

# 7. Team Structure & Responsibilities

| Role | Primary Responsibilities | MVP Deliverables |
| --- | --- | --- |
| Engineering Lead (Blockchain) | Protocol adapter architecture, Ponder setup, DB schema, indexer reliability | All 8 protocol adapters, DB schema, Redis cache, indexer monitoring |
| Full-Stack Engineer | REST API (Fastify), Next.js frontend, WebSocket server, API documentation | GET /tx, GET /address/txs endpoints, all frontend pages, WS server |
| Frontend Engineer | Next.js components, Tailwind/shadcn, Chain Flow Map (D3.js), mobile optimization | All UI components, Chain Flow Map animation, mobile responsive design |
| Product Manager (0xOse) | Product spec, protocol prioritization, launch strategy, community, analytics | This document, launch checklist, Discord setup, Product Hunt, Twitter launch |

## Working Agreements

- Weekly sprint cycle: Monday kickoff, Friday demo

- Daily async standup in Discord (3 bullets: done, doing, blocked)

- Protocol adapter PR: reviewed by Eng Lead before merge

- No feature scope additions after Week 6 without PM + Eng Lead approval

- On-call rotation: once live, 2-hour SLA for P0 issues

# 8. Post-MVP Roadmap (What Comes Next)

The MVP validates demand. Phase 2 builds retention and monetization. This is the plan if MVP succeeds (>1K WAU in 30 days):

| Phase | Timeline | Theme | Key Features | Revenue Target |
| --- | --- | --- | --- | --- |
| MVP (Phase 1) | Week 1-8 | Validate demand | 8 protocols, search, tx detail, chain explorer, Chain Flow Map, public API | $0 (free) |
| Phase 2 | Month 3-4 | Retain & Grow | Wallet portfolio, alerts (email), API key portal (Stripe), 6 more protocols, analytics dashboard | $2,000 MRR |
| Phase 3 | Month 5-6 | Monetize | Seraph Pro ($19/mo), webhook system, Pro API ($199/mo), 20+ protocols | $10,000 MRR |
| Phase 4 | Month 7-12 | Scale & Defend | EaaS white-label, enterprise compliance API pilot, entity labeling, mobile apps | $50,000 MRR |

The North Star Decision After 30 days, we review: are users returning because they genuinely track cross-chain txs regularly? If yes, build alerts and portfolio (Phase 2). If users come once and don't return, the problem isn't recurring enough — consider pivoting to the developer API as the primary product instead of the consumer explorer.

## 10 Things We Will NOT Build in the First Year

Clarity on what we're not building is as important as what we are. These are deliberate 'not-nows':

- A token (LENS or similar) — no token until $1M ARR and proven product-market fit

- A native mobile app (iOS/Android) — PWA is sufficient; save native for Phase 4

- A full compliance suite — enterprise sales takes 6+ months; focus on consumer first

- Social features (user profiles, follows, feeds) — not a social product

- A DEX aggregator or bridge aggregator — we observe, we don't facilitate transactions

- NFT or token-gating — no friction for free users

- B2B sales motion before $10K MRR — bottoms-up adoption first

- A prediction or trading signal layer — not an analytics product

- Blockchain-specific governance features — we are chain-neutral

- VC fundraising in Year 1 — validate first, raise on metrics not vision

Final Word The Seraph MVP succeeds by being the fastest, most complete, and most consumer-friendly way to find any cross-chain transaction. Ship in 8 weeks. Launch publicly. Measure retention. Double down on what works. The market has validated the gap — now we go build it.